## EXAMPLE Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART | [60 empty] | https://goo.gl/ejIdKR
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
SPRINT 5
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation |  | 309 | 309 | 0 |  |  |  |  | 100%
1.1 | Project Charter | Leon W | 40 | 40 | 0 |  | 2017-03-12 | 2017-03-15 | 4 | 100% | bar: WEEK 1 F to WEEK 2 F
1.1.1 | Project Charter Revisions | Kylie R | 25 | 25 | 0 |  | 2017-03-15 | 2017-03-16 | 2 | 100%
1.2 | Research | Pete S | 100 | 100 | 0 |  | 2017-03-15 | 2017-03-21 | 7 | 100% | bar: WEEK 2 M to WEEK 3 R
1.3 | Projections | Steve L | 60 | 60 | 0 |  | 2017-03-16 | 2017-03-22 | 7 | 100% | bar: WEEK 2 M to WEEK 3 R
1.4 | Stakeholders | Allen W | 40 | 40 | 0 |  | 2017-03-17 | 2017-03-22 | 6 | 100% | bar: WEEK 2 M to WEEK 3 R
1.5 | Guidelines | Malik M | 32 | 32 | 0 |  | 2017-03-18 | 2017-03-22 | 5 | 100% | bar: WEEK 2 M to WEEK 3 R
1.6 | Project Initiation | Malik M | 12 | 12 | 0 |  | 2017-03-23 | 2017-03-23 | 1 | 100% | bar: WEEK 3 F
2 | Project Definition and Planning |  | 210 | 110 | 100 |  |  |  |  | 52.38%
2.1 | Scope and Goal Setting | Steve L | 80 | 70 | 10 |  | 2017-03-24 | 2017-03-28 | 5 | 87.5% | bar: WEEK 4 M to WEEK 5 F
2.2 | Budget | Allen W | 60 | 40 | 20 |  | 2017-03-29 | 2017-04-02 | 5 | 66.67%
2.3 | Communication Plan | Malik M | 40 | 0 | 40 |  |  |  | 1 | 0%
2.4 | Risk Management | Malik M | 30 | 0 | 30 |  |  |  | 1 | 0%
3 | Project Launch and Execution |  | 66 | 0 | 66 |  |  |  |  | 0%
3.1 | Status and Tracking | Pete S | 20 | 0 | 20 |  |  |  | 1 | 0%
3.2 | KPIs | Leon W | 20 | 0 | 20 |  |  |  | 1 | 0%
3.2.1 | Monitoring | Kylie R | 8 | 0 | 8 |  |  |  | 1 | 0%
3.2.2 | Forecasts | Kylie R | 12 | 0 | 12 |  |  |  | 1 | 0%
3.3 | Project Updates | Pete S | 4 | 0 | 4 |  |  |  | 1 | 0%
3.3.1 | Chart Updates | Malik M | 2 | 0 | 2 |  |  |  | 1 | 0%
4 | Project Performance/Monitoring |  | 32 | 0 | 32 |  |  |  |  | 0%
4.1 | Project Objectives | Steve L | 8 | 0 | 8 |  |  |  | 1 | 0%
4.2 | Quality Deliverables | Allen W | 12 | 0 | 12 |  |  |  | 1 | 0%
4.3 | Effort and Cost Tracking | Malik M | 8 | 0 | 8 |  |  |  | 1 | 0%
4.4 | Project Performance | Malik M | 4 | 0 | 4 |  |  |  | 1 | 0%
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 617 | 419 | 198 | 60 | 10.2833 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 617 | 606.7167 | 596.4333 | 586.15 | 575.8667 | 565.5833 | 555.3 | 545.0167 | 534.7333 | 524.45 | 514.1667 | 503.8833 | 493.6 | 483.3167 | 473.0333 | 462.75 | 452.4667 | 442.1833 | 431.9 | 421.6167 | 411.3333 | 401.05 | 390.7667 | 380.4833 | 370.2 | 359.9167 | 349.6333 | 339.35 | 329.0667 | 318.7833 | 308.5 | 298.2167 | 287.9333 | 277.65 | 267.3667 | 257.0833 | 246.8 | 236.5167 | 226.2333 | 215.95 | 205.6667 | 195.3833 | 185.1 | 174.8167 | 164.5333 | 154.25 | 143.9667 | 133.6833 | 123.4 | 113.1167 | 102.8333 | 92.55 | 82.2667 | 71.9833 | 61.7 | 51.4167 | 41.1333 | 30.85 | 20.5667 | 10.2833
[10 empty] | ESTIMATE | 617 | 609 | 589 | 559 | 519 | 499 | 488 | 472 | 430 | 385 | 365 | 355 | 339 | 315 | 267 | 247 | 243 | 238 | 234 | 226 | 218 | 213 | 208 | 203 | 200 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 15968
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | WEEK 1 M: 8; WEEK 1 T: 20; WEEK 1 W: 30; WEEK 1 R: 40; WEEK 1 F: 20; WEEK 2 M: 11; WEEK 2 T: 16; WEEK 2 W: 42; WEEK 2 R: 45; WEEK 2 F: 20; WEEK 3 M: 10; WEEK 3 T: 16; WEEK 3 W: 24; WEEK 3 R: 48; WEEK 3 F: 20; WEEK 4 M: 4; WEEK 4 T: 5; WEEK 4 W: 4; WEEK 4 R: 8; WEEK 4 F: 8; WEEK 5 M: 5; WEEK 5 T: 5; WEEK 5 W: 5; WEEK 5 R: 3; WEEK 5 F: 2 | 419
[10 empty] | HRS REMAINING | 609 | 589 | 559 | 519 | 499 | 488 | 472 | 430 | 385 | 365 | 355 | 339 | 315 | 267 | 247 | 243 | 238 | 234 | 226 | 218 | 213 | 208 | 203 | 200 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 15549
CLICK HERE TO CREATE GANTT CHART TEMPLATES IN SMARTSHEET

## BLANK Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
SPRINT 5
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Setup |  | 102 | 102 | 0 |  |  |  |  | 100%
1.1 | Docker Environment Setup | Andrii Voznuk | 90 | 90 | 0 |  | 2024-10-21 | 2024-11-01 | 12 | 100% | bar: WEEK 1 M to WEEK 3 W
1.2 | Chess Game Repository Creation | Viacheslav Varnavskyi | 2 | 2 | 0 |  | 2024-10-21 | 2024-10-21 | 1 | 100% | bar: WEEK 1 M
1.3 | User Authentication Design | Viacheslav Varnavskyi | 10 | 10 | 0 |  | 2024-11-01 | 2024-11-02 | 2 | 100% | bar: WEEK 1 T to WEEK 1 W
2 | User Authentication |  | 38 | 38 | 0 |  |  |  |  | 100%
2.1 | User Registration | Viacheslav Varnavskyi | 16 | 16 | 0 |  | 2024-11-04 | 2024-11-04 | 1 | 100% | bar: WEEK 3 R
2.2 | User Login | Andrii Voznuk | 12 | 12 | 0 |  | 2024-11-05 | 2024-11-06 | 2 | 100% | bar: WEEK 3 R to WEEK 3 F
2.3 | Logout Functionality | Viacheslav Varnavskyi | 10 | 10 | 0 |  | 2024-11-06 | 2024-11-07 | 2 | 100% | bar: WEEK 4 M to WEEK 4 T
3 | Game Room Management |  | 95 | 95 | 0 |  |  |  |  | 100%
3.1 | Create Game Room | Viacheslav Varnavskyi | 60 | 60 | 0 |  | 2024-11-07 | 2024-11-14 | 8 | 100% | bar: WEEK 4 W to WEEK 5 F
3.2 | List Available Rooms | Andrii Voznuk | 10 | 10 | 0 |  | 2024-11-14 | 2024-11-15 | 2 | 100% | bar: WEEK 4 W to WEEK 4 R
3.2.1 | Join Game Room | Andrii Voznuk | 25 | 25 | 0 |  | 2024-11-18 | 2024-11-20 | 3 | 100% | bar: WEEK 4 F to WEEK 5 F
4 | Chess Game Logic |  | 86 | 86 | 0 |  |  |  |  | 100%
4.1 | Chess Board Setup | Andrii Voznuk | 20 | 20 | 0 |  | 2024-11-20 | 2024-11-22 | 3 | 100%
4.2 | Chess Piece Movement | Viacheslav Varnavskyi | 41 | 41 | 0 |  | 2024-11-23 | 2024-11-26 | 4 | 100% | bar: WEEK 5 M to WEEK 6 R
4.3 | Turn-Based Gameplay | Andrii Voznuk | 10 | 10 | 0 |  | 2024-11-26 | 2024-11-27 | 2 | 100% | bar: WEEK 5 M to WEEK 6 T
4.4 | Draw and Resign Functionality | Andrii Voznuk | 15 | 15 | 0 |  | 2024-11-28 | 2024-11-29 | 2 | 100% | bar: WEEK 6 W to WEEK 6 R
4.5 | Time Control Implementation | Viacheslav Varnavskyi | 20 | 20 | 0 |  | 2024-11-29 | 2024-12-02 | 4 | 100% | bar: WEEK 6 F to WEEK 7 W
4.6 | Timer Expiry Logic | Andrii Voznuk | 10 | 10 | 0 |  | 2024-12-27 | 2024-12-28 | 2 | 100% | bar: WEEK 6 F to WEEK 7 M
5 | Bot realization |  | 9 | 9 | 0 |  |  |  |  | 100%
5.1 | BOT Integration | Andrii Voznuk | 7 | 7 | 0 |  | 2025-01-18 | 2025-01-18 | 1 | 100% | bar: WEEK 7 T
5.2 | Premoves Implementation | Andrii Voznuk | 2 | 2 | 0 |  | 2025-01-31 | 2025-01-31 | 1 | 100% | bar: WEEK 7 W
6 | Statistics Collection |  | 50 | 0 | 50 |  |  |  |  | 0%
6.1 | Game Statistics Collection | Andrii Voznuk | 30 | 0 | 30 |  |  |  | 1 | 0%
6.2 | User Progress Dashboard | Viacheslav Varnavskyi | 20 | 0 | 20 |  |  |  | 1 | 0%
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 410 | 360 | 0 | 60 | 6.8333 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 410 | 403.1667 | 396.3333 | 389.5 | 382.6667 | 375.8333 | 369 | 362.1667 | 355.3333 | 348.5 | 341.6667 | 334.8333 | 328 | 321.1667 | 314.3333 | 307.5 | 300.6667 | 293.8333 | 287 | 280.1667 | 273.3333 | 266.5 | 259.6667 | 252.8333 | 246 | 239.1667 | 232.3333 | 225.5 | 218.6667 | 211.8333 | 205 | 198.1667 | 191.3333 | 184.5 | 177.6667 | 170.8333 | 164 | 157.1667 | 150.3333 | 143.5 | 136.6667 | 129.8333 | 123 | 116.1667 | 109.3333 | 102.5 | 95.6667 | 88.8333 | 82 | 75.1667 | 68.3333 | 61.5 | 54.6667 | 47.8333 | 41 | 34.1667 | 27.3333 | 20.5 | 13.6667 | 6.8333
[10 empty] | ESTIMATE | 410 | 394 | 378 | 370 | 362 | 354 | 349 | 341 | 333 | 325 | 318 | 310 | 304 | 297 | 281 | 273 | 265 | 257 | 248 | 236 | 221 | 205 | 190 | 176 | 166 | 161 | 145 | 134 | 122 | 106 | 90 | 74 | 58 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 9603
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | WEEK 1 M: 16; WEEK 1 T: 16; WEEK 1 W: 8; WEEK 1 R: 8; WEEK 1 F: 8; WEEK 2 M: 5; WEEK 2 T: 8; WEEK 2 W: 8; WEEK 2 R: 8; WEEK 2 F: 7; WEEK 3 M: 8; WEEK 3 T: 6; WEEK 3 W: 7; WEEK 3 R: 16; WEEK 3 F: 8; WEEK 4 M: 8; WEEK 4 T: 8; WEEK 4 W: 9; WEEK 4 R: 12; WEEK 4 F: 15; WEEK 5 M: 16; WEEK 5 T: 15; WEEK 5 W: 14; WEEK 5 R: 10; WEEK 5 F: 5; WEEK 6 M: 16; WEEK 6 T: 11; WEEK 6 W: 12; WEEK 6 R: 16; WEEK 6 F: 16; WEEK 7 M: 16; WEEK 7 T: 16; WEEK 7 W: 8 | 360
[10 empty] | HRS REMAINING | 394 | 378 | 370 | 362 | 354 | 349 | 341 | 333 | 325 | 318 | 310 | 304 | 297 | 281 | 273 | 265 | 257 | 248 | 236 | 221 | 205 | 190 | 176 | 166 | 161 | 145 | 134 | 122 | 106 | 90 | 74 | 58 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 9243
CLICK HERE TO CREATE SCRUM PROJECT MANAGEMENT GANTT CHART TEMPLATES IN SMARTSHEET

## Release Backlog
SCRUM PROJECT MANAGEMENT GANTT CHART
RELEASE BACKLOG
PRIORITY | SPRINT | FUNCTIONALITY | TASK TITLE | TASK DESCRIPTION | TASK OWNER | WORK ESTIMATE IN HOURS | STATUS | NOTES | STATUS KEY | WORK ESTIMATE IN HOURS
1 | 1 |  | Docker Environment Setup |  | Andrii Voznuk | 90 | Completed |  | Not Started | 1
1 | 1 |  | Chess Game Repository Creation |  | Viacheslav Varnavskyi | 2 | Completed |  | In Progress | 2
2 | 1 |  | User Authentication Design |  | Viacheslav Varnavskyi | 10 | Completed |  | Completed | 4
3 | 2 |  | User Registration |  | Viacheslav Varnavskyi | 16 | Completed |  |  | 7
3 | 2 |  | User Login |  | Andrii Voznuk | 12 | Completed |  |  | 8
3 | 2 |  | Logout Functionality |  | Viacheslav Varnavskyi | 10 | Completed |  |  | 10
3 | 3 |  | Create Game Room |  | Viacheslav Varnavskyi | 60 | Completed |  |  | 12
3 | 3 |  | List Available Rooms |  | Andrii Voznuk | 10 | Completed |  |  | 15
3 | 3 |  | Join Game Room |  | Andrii Voznuk | 15 | Completed |  |  | 16
3 | 4 |  | Chess Board Setup |  | Andrii Voznuk | 20 | Completed |  |  | 20
3 | 4 |  | Chess Piece Movement |  | Viacheslav Varnavskyi | 41 | Completed |  |  | 24
3 | 4 |  | Turn-Based Gameplay |  | Andrii Voznuk | 10 | Completed |  |  | 25
3 | 4 |  | Draw and Resign Functionality |  | Andrii Voznuk | 15 | Completed |  |  | 30
3 | 4 |  | Time Control Implementation |  | Viacheslav Varnavskyi | 20 | Completed |  |  | 40
3 | 4 |  | Timer Expiry Logic |  | Andrii Voznuk | 10 | Completed |  |  | 41
4 | 5 |  | BOT Integration |  | Andrii Voznuk | 8 | Completed |  |  | 60
5 | 5 |  | Premoves Implementation |  | Andrii Voznuk | 2 | Completed |  |  | 80
4 | 6 |  | Game Statistics Collection |  | Andrii Voznuk | 30 | In Progress |  |  | 90
3 | 6 |  | User Progress Dashboard |  | Viacheslav Varnavskyi | 20 | Not Started

## User Stories or Tasks
SCRUM PROJECT MANAGEMENT GANTT CHART
USER STORIES or TASKS
TASK TITLE | TASK DESCRIPTION | ADDED BY | DATED ADDED
Docker Environment Setup | Set up Docker containers for the application, including frontend, backend, and database services. | Andrii Vozniuk | 21.10.2024
Chess Game Repository Creation | Create a GitHub repository for the project and initialize the basic structure for the chess platform. | Andrii Vozniuk | 21.10.2024
User Authentication Design | Design the user registration and login system, including JWT token implementation for session persistence. | Andrii Vozniuk | 01.11.2024
User Registration | Implement user registration functionality, including email validation and password hashing. | Andrii Vozniuk | 01.11.2024
User Login | Implement user login functionality with session persistence using cookies or local storage. | Andrii Vozniuk | 01.11.2024
Logout Functionality | Implement logout functionality to clear user sessions. | Andrii Vozniuk | 01.11.2024
Create Game Room | Implement functionality for users to create a game room and wait for opponents. | Viacheslav Varnavskyi | 07.11.2024
List Available Rooms | Implement a list of available rooms where users can join or connect to friends. | Viacheslav Varnavskyi | 07.11.2024
Join Game Room | Implement functionality for users to join a game room and start a match. | Andrii Vozniuk | 15.11.2024
Chess Board Setup | Implement the chessboard UI and initialize pieces according to standard rules. | Viacheslav Varnavskyi | 17.11.2024
Chess Piece Movement | Implement chess piece movement logic following FIDE regulations. | Viacheslav Varnavskyi | 17.11.2024
Turn-Based Gameplay | Implement turn-based gameplay where players take turns making moves. | Viacheslav Varnavskyi | 12.12.2024
Draw and Resign Functionality | Implement functionality for users to offer a draw or resign from the game. | Viacheslav Varnavskyi | 12.12.2024
Time Control Implementation | Implement time controls (Bullet, Blitz, Rapid, Classical) with countdown timers. | Viacheslav Varnavskyi | 12.12.2024
Timer Expiry Logic | Implement logic to declare a winner if the opponent’s time runs out. | Viacheslav Varnavskyi | 12.12.2024
BOT Integration | Implement functionality to play against a BOT with adjustable complexity levels. | Viacheslav Varnavskyi | 04.01.2025
Premoves Implementation | Implement premove functionality to allow users to queue moves in advance. | Viacheslav Varnavskyi | 04.01.2025
Game Statistics Collection | Implement functionality to collect game statistics (e.g., wins, losses, draws, time spent). | Andrii Vozniuk | 07.01.2025
User Progress Dashboard | Create a dashboard for users to view their game statistics and progress over time. | Andrii Vozniuk | 07.01.2025